## Sheet1
	min	max
GENERAL TASKS
Message queue framework research + experiment	3 days	5 days
Which languages..?
	3 days	5 days

CONTROLLER TASKS
Web API design + implementation	2 days	5 days	* ”rewire” existing UI
Algorithm Execution Service	1 week	2 weeks
Algorithm Execution Interface	1 week	2 weeks
Task Handler Service	1 week	2 weeks
	~3.5 weeks	~7 weeks

WORKER TASKS
Web API design + implementation	3 days	5 days	* partially done
Requests Handler Service	1 week	2 weeks
Udf Execution Service	1 week	2 weeks	* Jason required / * Hardcoded for demo ??
DB Interface Service	2 days	4 days
	~3 weeks	~5 weeks

ALGORITHM TASKS
Implentation of algs for the new system			* Jason